## Sheet1
Weekly Logbook - CNU Rowing Club Web Application
| Date | Time | Time spent | Total Time | What progress did you make last week? | What progress do you plan on making this week? | What/if any changes will you expect from your proposal?
Week 1
[5 empty] | This week I have worked on planning and sketching my web application as well as wireframing. I began setting up my development environment. I also began researching and planning for my database based on the user interactions and functionality I have outlined for my application. I have decided what framework I am using for the front end. I plan to use vue.js and have begun experimenting with it. Admittedly, I have not gotten as much done this week as I had hoped. | Hopefully going forward I can get a little more done this week and get on track to where I want to be. I expect to begin building the database and spend around 4 hours on this. I plan to spend at least 3 more hours researching and beginning to learn frameworks. My development environment is not fully set up, and I expect it will take me another hour or so to get that where I want it. | I believe I stated that I would potentially be using React as my front end framework. This has now changed to vue.js.
Planning | 2021-02-11 | 10:44am-11:28am, 11:44am-12:16pm | 44:04, 31:45 | 1 hr, 15 min
Planning/Research (DB, wireframing) | 2021-02-14 | 6:09pm-6:56pm, 8:22pm-9:17pm | 47:43, 55:02 | 1 hr, 42 min
Planning - Wireframing, Researching Framework | 2021-02-16 | 11:01am-12:05pm, 1:58pm-2:22pm | 1:05:53, 24:04 | 1 hr, 30 min
Setting up Development Environment | 2021-02-16 | 12:06pm-12:24pm, 3:23pm-3:53pm, 9:09pm-9:14pm | 17:59, 30:04, 4:59 | 53 min
Week 2
[5 empty] | This week I have worked on database design and implementation using AWS Amplify data modeling. I met with Dr. Almalag to discuss my database design. I finished configuring my development environment, but I may have to make minor adjustments to it as I add more to the project. I spent about 2 hours learning vue.js in tutorials as well as refreshing myself on JavaScript. | In the upcoming week, I expect to spend 2 hours beginning to set up a log in page. I’m having an issue with my front end showing up at the AWS web page, so I would like to get that fixed. Hopefully it will take less than an hour. I also plan to spend one or two hours making sure the database can interact with the front end. I expect to spend one hour designating what privileges different levels of users have. The users have a tag in the database (status) that will tell the application what actions they have access to. | I have at this point decided not to allow users to set availability. Most of the events the rowing club has are practice, and there is no need for users to mark availability for these. (Practice is at 5:00am, everyone is available.) Users will still be able to view events. E-board members will still take attendance at events/practices.
Debugging (fixing Git Issue) | 2021-02-16 | 9:40pm-9:54pm | 14:06 | 14 min
Setting up Development Environment | 2021-02-16 | 9:54pm-10:15pm | 20:39 | 20 min
Database Planning | 2021-02-16 | 10:22pm-10:34pm | 12:22 | 12 min
Database Design (ER Diagram, meeting) | 17-Feb, 18-Feb | 9:20pm-9:28pm, 2:00pm-2:42pm | 18:00, 42:00 | 1 hr
Database (ER Diagram, implementation) | 2021-02-21 | 5:47pm-5:57pm, 5:57pm-6:14pm | 9:40, 16:39 | 26 min
Front End (Vue.js tutorial) | 2021-02-21 | 6:14pm-6:53pm | 38:54 | 39 min
Database | 2021-02-22 | 11:20am-11:35am | 14:44 | 15 min
Front End (Vue.js tutorial) | 2021-02-23 | 3:29pm-4:49pm | 1:11 | 1 hr, 11 min
Setting up Development Environment | 2021-02-23 | 9:57pm-10:16pm | 19:12 | 19 min
Week 3
Front End (Vue.js tutorial) | 2021-02-26 | 3:26pm-4:21pm | 55:07 | 55 min
Set Up Log In Page | 2021-02-28 | 12:59pm-1:38pm, 6:25pm-7:07pm, 7:28pm-7:59pm | 39:15, 42:05, 31:22 | 1 hr, 52 min
Connect front end to database
Create roles with varying levels of access
Debugging
Week 4
Refine Login Page
Set up home page/ menu to access other features
Debugging
Week 5
Set up Scheduling page
Set up scheduling functionality
Debgging
Week 6
Set up Roster Front End
Set up Roster functionality
Debugging
Week 7
Set up Attendence page
Configure attendence functionality
Debugging
Week 8
Finish configuring application functionality
Debugging
Week 9
UI Improvement
Debugging
Week 10
Testing/ fine tuning
Debugging
Creating Final Presentation