## Project Planner
CNU Rowing Club Web Application Gannt Chart
Period Highlight: | 1 |  | Plan Duration |  |  | Actual Start |  |  |  | % Complete |  |  |  | Actual (beyond plan) |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Researching Frameworks | 1 | 1 | 1 | 2 | 100%
Databse Building | 1 | 1 | 1 | 2 | 100%
Additional Research | 1 | 1 | 1 | 3 | 100%
Database Set Up | 2 | 1 | 2 | 3 | 100%
Research | 2 | 1 | 2 | 3 | 100%
Debugging | 2 | 1 | 0 | 0 | 0%
Connect front end to database | 3 | 1 | 3 | 3 | 100%
Set Up Log In Page | 3 | 1 | 3 | 7 | 90%
Create roles with varying levels of access | 3 | 1 | 8 | 2 | 100%
Debugging | 3 | 1 | 0 | 0 | 0%
Refine Login Page | 4 | 1 | 8 | 2 | 80%
Set up home page/ menu to access other features | 4 | 1 | 4 | 3 | 95%
Debugging | 4 | 1 | 0 | 0 | 0%
Set up Scheduling page | 5 | 1 | 4 | 6 | 85%
Set up scheduling functionality | 5 | 1 | 7 | 3 | 85%
Debgging | 5 | 1 | 0 | 0 | 0%
Set up Roster Front End | 6 | 1 | 5 | 4 | 90%
Set up Roster functionality | 6 | 1 | 8 | 2 | 100%
Debugging | 6 | 1 | 0 | 0 | 0%
Set up Attendence page | 7 | 1 | 5 | 4 | 80%
Configure attendence functionality | 7 | 1 | 9 | 1 | 80%
Debugging | 7 | 1 | 0 | 0 | 0%
Finish configuring application functionality | 8 | 1 | 8 | 3 | 80%
Debugging | 8 | 1 | 0 | 0 | 0%
UI Improvement | 9 | 1 | 9 | 2 | 10%
Debugging | 9 | 1 | 0 | 0 | 0%
Testing/ fine tuning | 10 | 1 | 9 | 2 | 10%
Debugging | 10 | 1 | 0 | 0 | 0%
Creating Final Presentation | 10 | 1 | 9 | 2 | 5%