## Sheet1
Weekly Logbook - CNU Rowing Club Web Application
| Date | Time | Time spent | Total Time | What progress did you make last week? | What progress do you plan on making this week? | What/if any changes will you expect from your proposal?
Week 1
[5 empty] | This week I have worked on planning and sketching my web application as well as wireframing. I began setting up my development environment. I also began researching and planning for my database based on the user interactions and functionality I have outlined for my application. I have decided what framework I am using for the front end. I plan to use vue.js and have begun experimenting with it. Admittedly, I have not gotten as much done this week as I had hoped. | Hopefully going forward I can get a little more done this week and get on track to where I want to be. I expect to begin building the database and spend around 4 hours on this. I plan to spend at least 3 more hours researching and beginning to learn frameworks. My development environment is not fully set up, and I expect it will take me another hour or so to get that where I want it. | I believe I stated that I would potentially be using React as my front end framework. This has now changed to vue.js.
Planning | 2021-02-11 | 10:44am-11:28am, 11:44am-12:16pm | 44:04, 31:45 | 1 hr, 15 min
Planning/Research (DB, wireframing) | 2021-02-14 | 6:09pm-6:56pm, 8:22pm-9:17pm | 47:43, 55:02 | 1 hr, 42 min
Planning - Wireframing, Researching Framework | 2021-02-16 | 11:01am-12:05pm, 1:58pm-2:22pm | 1:05:53, 24:04 | 1 hr, 30 min
Setting up Development Environment | 2021-02-16 | 12:06pm-12:24pm, 3:23pm-3:53pm, 9:09pm-9:14pm | 17:59, 30:04, 4:59 | 53 min
Week 2
[5 empty] | This week I have worked on database design and implementation using AWS Amplify data modeling. I met with Dr. Almalag to discuss my database design. I finished configuring my development environment, but I may have to make minor adjustments to it as I add more to the project. I spent about 2 hours learning vue.js in tutorials as well as refreshing myself on JavaScript. | In the upcoming week, I expect to spend 2 hours beginning to set up a log in page. I’m having an issue with my front end showing up at the AWS web page, so I would like to get that fixed. Hopefully it will take less than an hour. I also plan to spend one or two hours making sure the database can interact with the front end. I expect to spend one hour designating what privileges different levels of users have. The users have a tag in the database (status) that will tell the application what actions they have access to. | I have at this point decided not to allow users to set availability. Most of the events the rowing club has are practice, and there is no need for users to mark availability for these. (Practice is at 5:00am, everyone is available.) Users will still be able to view events. E-board members will still take attendance at events/practices.
Debugging (fixing Git Issue) | 2021-02-16 | 9:40pm-9:54pm | 14:06 | 14 min
Setting up Development Environment | 2021-02-16 | 9:54pm-10:15pm | 20:39 | 20 min
Database Planning | 2021-02-16 | 10:22pm-10:34pm | 12:22 | 12 min
Database Design (ER Diagram, meeting) | 17-Feb, 18-Feb | 9:20pm-9:28pm, 2:00pm-2:42pm | 18:00, 42:00 | 1 hr
Database (ER Diagram, implementation) | 2021-02-21 | 5:47pm-5:57pm, 5:57pm-6:14pm | 9:40, 16:39 | 26 min
Front End (Vue.js tutorial) | 2021-02-21 | 6:14pm-6:53pm | 38:54 | 39 min
Database | 2021-02-22 | 11:20am-11:35am | 14:44 | 15 min
Front End (Vue.js tutorial) | 2021-02-23 | 3:29pm-4:49pm | 1:11 | 1 hr, 11 min
Setting up Development Environment | 2021-02-23 | 9:57pm-10:16pm | 19:12 | 19 min
Week 3
[5 empty] | This week I have continued learning Vue.js. I have also started watching and reading tutorials and playing around to create a login page. I have spent some time working on fixing my AWS Amplify web page display issue to no avail. Additionally, I somehow broke my virtual machine (more specifically, I tried to give it more memory and now it won’t boot), so I am in the process of reconfiguring that whole situation. | In the upcoming week, I expect to finish the login page set up. The login page is already taking me longer than expected, so I will probably spend at least two more hours on it. I need to basically reset up my entire virtual machine/development environment, because I broke it. That will probably take about an hour or less. Additionally, I truly need to fix this AWS Amplify issue, which I expect to take around an hour. Last week I said I would work on the database front end interaction for about an hour or two. I did not get to that last week, so I need to work on it this week. I also need to work on the user privilege for an hour, which I also did not get to last week. If I can, I would also like to spend an hour or two to start setting up the home page. | I do not have any changes this week.
Front End (Vue.js tutorial) | 2021-02-26 | 3:26pm-4:21pm | 55:07 | 55 min
Set Up Log In Page (Research/Tutorials) | 2021-02-28 | 12:59pm-1:38pm, 6:25pm-7:07pm, 7:28pm-7:59pm | 39:15, 42:05, 31:22 | 1 hr, 52 min
More Login Page Research | 2021-03-02 | 12:10pm-12:26pm | 15:48 | 15 min
Updating Logbook | 2021-03-01 | 12:22pm-1:00pm, 2:49pm-2:56pm | 48:00, 6:30 | 45 min
Week 4
[5 empty] | This past week, I set up a new virtual machine to replace the old one I broke. This included redownloading everything for developing my web application. Additionally, I began building a home page for my web application. I also created a separate page for the schedule that basically has nothing in it yet. I spent some time trying to figure out how to get my front end set up to pull information from the back end database. This process included reaching and experimenting. Lastly, this week, I attempted to fix my AWS Amplify issue. Somehow I still have not figured it out, although I feel I am closer to a solution. | In the upcoming week, I expect to put some time into the login page. Most of the time I already spent on the login page was viewing tutorials and not making a whole lot of real progress, so I definitely need to spend more time on this, probably at least 2 hours. I still need to fix this AWS Amplify issue. Honestly no idea how long this is going to take, but I anticipate banging my head against this wall for another hour at least. (Alternatively, I’m considering exploring more well known AWS options.) I spent some time working toward connecting the front end to the database, and this upcoming week I expect to spend another hour or two on this. Lastly, I intend to spend at least an hour refining the home page and an hour putting together the schedule page. | I do not have any changes this week.
Resetting up Virtual Machine/ Development Environment | 8,9-Mar | 6:21pm-7:10pm, 9:48am-10:01am | 49:40, 12:38 | 1 hr
Creating home page | 2021-03-08 | 7:35pm-8:14pm | 38:51 | 40 min
Connecting front end to database (Research) | 2021-03-09 | 10:04am-10:24am, 10:43am-11:32am | 19:57, 48:52 | 1 hr, 10 min
Fixing AWS display issue | 2021-03-09 | 12:15pm-12:27pm, 1:51pm-2:30pm | 12:28, 38:52 | 40 min
Setting up home page | 2021-03-09 | 3:19pm-3:48pm | 29 | 29 min
Week 5
[5 empty] | This past week, I spent a log of time trying to get things to work without succeeding. I fixed my AWS “Access denied” issue in 15 minutes with the help of an alum who is more familiar with AWS. With this issue fixed, the web page is displaying on the AWS hosted link. However, the css and/or vue.js is not displaying correctly so I spend about 50 minutes trying to figure out how to fix this issue. I spent an hour and 40 minutes building the home page for the web app. I also created the other pages in about 35 minutes. Part of that time was trying to get the back button to work. I spent another 47 minutes researching how to create a login page and not actually creating anything working. I also spend 2 and a half hours working on connecting the front end to the database. Part of this time was spent googling and going down various rabbit holes of things that I don’t think I actually need. I eventually got to php and attempted to connect to the database, but I cannot get the php to work properly. Lastly, I spent about half an hour updating my more detailed logbook and an hour and a half working on my Intermediate Presentation #1. | In the upcoming week, I really need to get some kind of login page up. I expect to spend 2 hours on this part. Ideally, I can also solve my AWS css/vue issue in under an hour and get the hosted web page to match the local one. Additionally, I need to spend an hour or so getting the php working on my machine to get the database connected and working. Once I get the database connection working, I intend to spend at least an hour setting up the schedule page to load in events for the users to see. | I do not have any changes this week.
Fixing AWS display issue | 2021-03-10 | 5:05pm-5:20pm | 15 | 15 min
Setting up home page | 2021-03-10 | 5:21pm-5:50pm | 29 | 29 min
Connecting front end to database (Research) | 2021-03-12 | 11:45am-11:56am | 11 | 11 min
Attempting to get vue.js working on AWS display | 2021-03-13 | 9:42am-10:31am | 49 | 50 min
Login Page (research/experimentation) | 2021-03-13 | 10:31am-10:55am | 24 | 24 min
Home page + button functionality | 2021-03-13 | 1:08pm-1:56pm, 2:17pm-2:42pm, 3:10pm-3:46pm | 48, 24, 35 | 1 hr, 40 min
Login page experimentation | 2021-03-14 | 9:58am-10:21am | 23 | 23 min
connecting front end to database (trying to get php to work) | 2021-03-14 | 11:41am-12:37pm, 1:04pm-2:04pm, 2:11pm-2:14pm, 4:08pm-4:27pm | 56, 60, 3, 19 | 2 hr, 10 min
Updating Logbook | 2021-03-14 | 10:07pm-10:42pm | 35 | 35 min
Intermediate Presentation 1 | 2021-03-14 | 10:41pm-11:13pm | 45 | 45 minutes
Week 6
[5 empty] | This past week, I spent much less time on this project than I intended. I am running into issues everywhere with just not knowing what I’m doing, and not being able to progress as a result. I spent some time trying to get php working by setting up a webserver, something I should have probably done weeks ago. I also spent time setting up bootstrap css and trying to get that working with my project. Lastly, I spent some time setting up a login page front end. | In the upcoming week, I expect to spend an hour or two setting up a webserver and getting php to work so I can connect to my database. I also plan to spend an hour finishing setting up bootstrap and hopefully getting my AWS hosted web page to match my local file. Then, I need to spend at least 4 hours working on the functionality portions of this web app starting with the scheduling page. I am quite behind at this point, so I need to put in work to catch up. | I do not have any changes this week.
Working on PHP | 2021-03-23 | 1:43pm-2:34pm, 5:52pm-6:14pm | 50, 21 | 1 hr, 11 min
Setting up bootstrap css | 2021-03-23 | 7:34pm-8:20pm | 45 | 45 minutes
work on login page | 2021-03-23 | 8:20pm-8:36pm | 16 | 16 minutes
Week 7
[5 empty] | This past week, I set up a web server for my web application. I spent about an hour and 12 minutes working on this webserver and getting the php code to work. I finally got the php code to work and pull database information before I promptly broke my webserver. Now, it does not display the web app at all. Originally, it displayed the home page, and would not navigate to the other pages when you click on the buttons. I was trying to fix that issue for a little over an hour when I broke the whole thing and it just gives me a “404 not found” error now. Additionally, I decided to ignore this issue for now to actually get some things done. Namely, I spent 2 hours and 14 minutes setting up a calendar on the schedule page to use for events. | In the upcoming week, I expect to spend at least another hour working on fixing my web server display issues and get the webserver to be able to navigate to each page that I’ve created. Additionally, I expect to spend an hour on the inevitable unknown problems that will pop up as a result of something I do. I plan to also spend 4-5 hours working on the scheduling calendar functionality as well as the roster and attendance pages. | I do not have any changes this week.
working on PHP | 2021-03-24 | 11:45am-11:56am, 12:23pm-12:25pm, 5:04pm-5:25pm | 11,2,20 | 35 minutes
working on PHP/setting Web Server | 2021-03-28 | 7:11pm-7:17pm | 5 | 5 minutes
working on database | 2021-03-30 | 12:42pm-1:08pm, 1:20pm-1:29pm | 25, 9 | 34 minutes
working on webserver | 2021-03-30 | 11:40am-11:44am, 12:31pm-12:42pm, 1:29pm-2:02pm, 3:20pm-3:39pm, 6:36pm-6:50pm | 4, 11, 33, 20, 14 | 1 hr, 21 min
Schedule Page | 2021-03-30 | 12:24pm-12:31pm, 3:39pm-5:47pm | 6, 127 | 2 hr, 13 min
Week 8
Working on webserver | 2021-03-31 | 4:21pm-4:49pm, 5:03pm-7:30pm | 38, 146 | 3 hr, 5 min
roster page | 2021-04-01 | 2:59pm-3:18pm, 3:29pm-4:05pm, 4:14pm-4:22pm | 19,36,7 | 1 hr, 57 min
attendance page | 2021-04-01 | 4:26pm-5:00pm, 5:01pm-5:06pm | 34, 5 | 39 minutes
settings page | 2021-04-01 | 5:06pm-5:22pm, 6:42pm-7:21pm | 16,28 | 54
attendance page | 2021-04-02 | 7:12pm-8:48pm | 96 | 1 hr, 36 min
Intermediate Presentation 2 | 2021-04-03 | 4:17pm-4:22pm, 4:38pm-5:18pm | 5,39 | 44 minutes
schedule page | 2021-04-03 | 6:30pm-7:48pm | 78 | 1 hr, 18 min
login page | 2021-04-04 | 4:30pm-4:50pm, 5:07pm-5:33pm, 6:22pm-7:00pm, 10:05pm-10:18pm | 20,26, 38, 13 | 1 hr, 36 min
Intermediate Presentation 2 | 2021-04-04 | 10:18pm-10:34pm, 10:34pm-11:44pm | 15, 69 | 1 hr, 24 min
schedule page | 2021-04-05 | 9:35pm-9:58pm | 23 | 23 minutes
login - send information to database | 2021-04-05 | 10:06pm-11:04pm | 57 | 57 minutes
login - password | 2021-04-05 | 11:10pm-11:16pm, 11:26pm-12:00am | 6,32 | 38 minutes
Week 9
[5 empty] | Since Intermediate Presentation 2, I have added a lot of functionality to my web app. The web app is just about to the point where it functionally does what I set out to accomplish. I spent about 23 minutes fixing the calendar display to correctly show the month starting on the right day. I spend about an hour setting up the login page to send information to the database (creating a new user). I spent about 40 minutes researching and reading up on how to do login on a web app and how to store user passwords. I had a database communication issue where one of the pages wasn’t able to send information to the database that took me an hour and 10 minutes to fix. Additionally, I spent about 5 and a half hours setting up the entire web app to remember the logged in user and customize the output to be specific to that user. This included setting up the settings page to pull in user information, let them change it, then update it in the database. It took me another hour and 16 minutes to make it so that certain features like create events and team attendance were only available to e-board users. I then spent about half an hour cleaning up my code to make it a little more readable. I added in a current events table and upcoming events table to the schedule page so users can see upcoming events which took about 2 hours. I also started going through the end of project requirements and prepping deliverables, which I spent a little over an hour on. I began creating my final presentation, and put almost an hour's worth of work into that. Finally, I created a new web server using Amazon Web Services EC2 rather than Amazon Amplify. I spent 2 and a half hours setting that up and getting my web application to show up. Then, I fixed some database issues to get the web app working again which took about an hour and a half. | In the upcoming week, I expect to spend a lot of time fine tuning. I’m going to continue working on my final presentation, hopefully spending no more than an hour on that. I would like to be able to submit my slides to early review by Friday. I will also likely spend another hour working on recording my final presentation. I would like to spend around an hour working on my capstone fair poster. I plan to continue preparing deliverables which will likely take another hour. I need to work on improving the user interface and visual design of my web application. This will likely take 2-3 hours of my time. I plan to spend around 2-3 hours debugging and fixing some minor issues here and there. Additionally, I intend to spend about an hour reviewing my proposal and making sure that my project meets the specifications I laid out in the beginning of the semester. | I have decided to use AWS EC2 to host my web application rather than AWS Amplify. My web server is running on Apache2 and the database was created using MySQL rather than DynamoDB. The client side scripting is done using PHP, and there is no Python code. (I said I would use Python and Django for backend code; that is no longer the case.) I am not using Amazon’s Rest API, nor am I using Amazon Cognito.
fixing database communication issue with PHP | 2021-04-07 | 12:16pm-12:25pm, 12:47pm-1:00pm, 4:09pm-4:16pm, 9:43pm-10:06pm, 11:06pm-11:25pm | 9,13,6,22,18 | 1 hr, 10 min
login user to entire app | 2021-04-07 | 11:25pm-11:50pm | 25 | 25 minutes
login user to entire app | 2021-04-08 | 9:47am-11:07am, 11:38am-12:14pm, 12:15pm-12:17pm | 120 | 2 hours
login user to entire app | 2021-04-09 | 11:44am-12:20pm, 12:47pm-12:52pm, 4:35pm-5:17pm | 36, 5,42 | 1 hr, 23 min
settings page and attendance login | 2021-04-09 | 5:18pm-6:05pm, 6:08pm-6:25pm | 47, 16 | 1 hr, 2 min
settings page | 2021-04-10 | 3:05pm-3:47pm | 42 | 42 minutes
eboard vs member view | 2021-04-10 | 4:04pm-5:18pm, 5:19pm-5:22pm | 73, 3 | 1 hr, 16 min
cleaning up code | 2021-04-10 | 5:23pm-5:58pm | 35 | 35 minutes
schedule page - today's events | 2021-04-11 | 5:21pm-5:56pm | 35 | 35 minutes
attendance - take attendance | 2021-04-11 | 5:56pm-7:44pm | 107 | 1 hr, 48 min
schedule - upcoming events | 2021-04-12 | 4:56pm-5:01pm | 5 | 5 minutes
Prepping final deliverables | 2021-04-12 | 5:42pm-5:57pm, 8:49pm-9:12pm, 10:15pm-10:49pm | 15, 22, 34 | 1 hr, 12 min
creating final presentation | 2021-04-12 | 10:50pm-11:44pm | 54 | 54 minutes
hosting public web server | 2021-04-13 | 2:57pm-5:14pm, 5:24pm-5:41pm | 137, 17 | 2 hr, 34 min
setting up database and fixing issues | 2021-04-13 | 9:10pm-10:34pm | 84 | 1 hr, 24 min
Week 10