## Sheet1
Weekly Logbook - CNU Rowing Club Web Application
| Date | Time | Time spent | Total Time | What progress did you make last week? | What progress do you plan on making this week? | What/if any changes will you expect from your proposal?
Week 1
[5 empty] | This week I have worked on planning and sketching my web application as well as wireframing. I began setting up my development environment. I also began researching and planning for my database based on the user interactions and functionality I have outlined for my application. I have decided what framework I am using for the front end. I plan to use vue.js and have begun experimenting with it. Admittedly, I have not gotten as much done this week as I had hoped. | Hopefully going forward I can get a little more done this week and get on track to where I want to be. I expect to begin building the database and spend around 4 hours on this. I plan to spend at least 3 more hours researching and beginning to learn frameworks. My development environment is not fully set up, and I expect it will take me another hour or so to get that where I want it. | I believe I stated that I would potentially be using React as my front end framework. This has now changed to vue.js.
Planning | 2021-02-11 | 10:44am-11:28am, 11:44am-12:16pm | 44:04, 31:45 | 1 hr, 15 min
Planning/Research (DB, wireframing) | 2021-02-14 | 6:09pm-6:56pm, 8:22pm-9:17pm | 47:43, 55:02 | 1 hr, 42 min
Planning - Wireframing, Researching Framework | 2021-02-16 | 11:01am-12:05pm, 1:58pm-2:22pm | 1:05:53, 24:04 | 1 hr, 30 min
Setting up Development Environment | 2021-02-16 | 12:06pm-12:24pm, 3:23pm-3:53pm, 9:09pm-9:14pm | 17:59, 30:04, 4:59 | 53 min
Week 2
[5 empty] | This week I have worked on database design and implementation using AWS Amplify data modeling. I met with Dr. Almalag to discuss my database design. I finished configuring my development environment, but I may have to make minor adjustments to it as I add more to the project. I spent about 2 hours learning vue.js in tutorials as well as refreshing myself on JavaScript. | In the upcoming week, I expect to spend 2 hours beginning to set up a log in page. I’m having an issue with my front end showing up at the AWS web page, so I would like to get that fixed. Hopefully it will take less than an hour. I also plan to spend one or two hours making sure the database can interact with the front end. I expect to spend one hour designating what privileges different levels of users have. The users have a tag in the database (status) that will tell the application what actions they have access to. | I have at this point decided not to allow users to set availability. Most of the events the rowing club has are practice, and there is no need for users to mark availability for these. (Practice is at 5:00am, everyone is available.) Users will still be able to view events. E-board members will still take attendance at events/practices.
Debugging (fixing Git Issue) | 2021-02-16 | 9:40pm-9:54pm | 14:06 | 14 min
Setting up Development Environment | 2021-02-16 | 9:54pm-10:15pm | 20:39 | 20 min
Database Planning | 2021-02-16 | 10:22pm-10:34pm | 12:22 | 12 min
Database Design (ER Diagram, meeting) | 17-Feb, 18-Feb | 9:20pm-9:28pm, 2:00pm-2:42pm | 18:00, 42:00 | 1 hr
Database (ER Diagram, implementation) | 2021-02-21 | 5:47pm-5:57pm, 5:57pm-6:14pm | 9:40, 16:39 | 26 min
Front End (Vue.js tutorial) | 2021-02-21 | 6:14pm-6:53pm | 38:54 | 39 min
Database | 2021-02-22 | 11:20am-11:35am | 14:44 | 15 min
Front End (Vue.js tutorial) | 2021-02-23 | 3:29pm-4:49pm | 1:11 | 1 hr, 11 min
Setting up Development Environment | 2021-02-23 | 9:57pm-10:16pm | 19:12 | 19 min
Week 3
[5 empty] | This week I have continued learning Vue.js. I have also started watching and reading tutorials and playing around to create a login page. I have spent some time working on fixing my AWS Amplify web page display issue to no avail. Additionally, I somehow broke my virtual machine (more specifically, I tried to give it more memory and now it won’t boot), so I am in the process of reconfiguring that whole situation. | In the upcoming week, I expect to finish the login page set up. The login page is already taking me longer than expected, so I will probably spend at least two more hours on it. I need to basically reset up my entire virtual machine/development environment, because I broke it. That will probably take about an hour or less. Additionally, I truly need to fix this AWS Amplify issue, which I expect to take around an hour. Last week I said I would work on the database front end interaction for about an hour or two. I did not get to that last week, so I need to work on it this week. I also need to work on the user privilege for an hour, which I also did not get to last week. If I can, I would also like to spend an hour or two to start setting up the home page. | I do not have any changes this week.
Front End (Vue.js tutorial) | 2021-02-26 | 3:26pm-4:21pm | 55:07 | 55 min
Set Up Log In Page (Research/Tutorials) | 2021-02-28 | 12:59pm-1:38pm, 6:25pm-7:07pm, 7:28pm-7:59pm | 39:15, 42:05, 31:22 | 1 hr, 52 min
More Login Page Research | 2021-03-02 | 12:10pm-12:26pm | 15:48 | 15 min
Updating Logbook | 2021-03-01 | 12:22pm-1:00pm, 2:49pm-2:56pm | 48:00, 6:30 | 45 min
Week 4
[5 empty] | This past week, I set up a new virtual machine to replace the old one I broke. This included redownloading everything for developing my web application. Additionally, I began building a home page for my web application. I also created a separate page for the schedule that basically has nothing in it yet. I spent some time trying to figure out how to get my front end set up to pull information from the back end database. This process included reaching and experimenting. Lastly, this week, I attempted to fix my AWS Amplify issue. Somehow I still have not figured it out, although I feel I am closer to a solution. | In the upcoming week, I expect to put some time into the login page. Most of the time I already spent on the login page was viewing tutorials and not making a whole lot of real progress, so I definitely need to spend more time on this, probably at least 2 hours. I still need to fix this AWS Amplify issue. Honestly no idea how long this is going to take, but I anticipate banging my head against this wall for another hour at least. (Alternatively, I’m considering exploring more well known AWS options.) I spent some time working toward connecting the front end to the database, and this upcoming week I expect to spend another hour or two on this. Lastly, I intend to spend at least an hour refining the home page and an hour putting together the schedule page. | I do not have any changes this week.
Resetting up Virtual Machine/ Development Environment | 8,9-Mar | 6:21pm-7:10pm, 9:48am-10:01am | 49:40, 12:38 | 1 hr
Creating home page | 2021-03-08 | 7:35pm-8:14pm | 38:51 | 40 min
Connecting front end to database (Research) | 2021-03-09 | 10:04am-10:24am, 10:43am-11:32am | 19:57, 48:52 | 1 hr, 10 min
Fixing AWS display issue | 2021-03-09 | 12:15pm-12:27pm, 1:51pm-2:30pm | 12:28, 38:52 | 40 min
Setting up home page | 2021-03-09 | 3:19pm-3:48pm | 29 | 29 min
Week 5
Fixing AWS display issue | 2021-03-10 | 5:05pm-5:20pm | 15 | 15 min
Setting up home page | 2021-03-10 | 5:21pm-5:50pm | 29 | 29 min
Connecting front end to database (Research) | 2021-03-12 | 11:45am-11:56am | 11 | 11 min
Attempting to get vue.js working on AWS display | 2021-03-13 | 9:42am-10:31am | 49 | 50 min
Login Page (research/experimentation) | 2021-03-13 | 10:31am-10:55am | 24 | 24 min
Home page + button functionality | 2021-03-13 | 1:08pm-1:56pm, 2:17pm-2:42pm, 3:10pm-3:46pm | 48, 24, 35 | 1 hr, 40 min
Login page experimentation | 2021-03-14 | 9:58am-10:21am | 23 | 23 min
connecting front end to database (trying to get php to work) | 2021-03-14 | 11:41am-12:37pm, 1:04pm-2:04pm, 2:11pm-2:14pm, 4:08pm-4:27pm | 56, 60, 3, 19 | 2 hr, 10 min
Updating Logbook | 2021-03-14 | 10:07pm-10:42pm | 35 | 35 min
Week 6
Set up Roster Front End
Set up Roster functionality
Debugging
Week 7
Set up Attendence page
Configure attendence functionality
Debugging
Week 8
Finish configuring application functionality
Debugging
Week 9
UI Improvement
Debugging
Week 10
Testing/ fine tuning
Debugging
Creating Final Presentation