## Sheet1
Weekly Logbook - CNU Rowing Club Web Application
| time spent | What progress did you make last week? | What progress do you plan on making this week? | What/if any changes will you expect from your proposal?
Week 1
Planning
Researching Frameworks
Databse Building
Additional Research
Week 2
Database Set Up
Research
Debugging
Week 3
Connect front end to database
Set Up Log In Page
Create roles with varying levels of access
Debugging
Week 4
Refine Login Page
Set up home page/ menu to access other features
Debugging
Week 5
Set up Scheduling page
Set up scheduling functionality
Debgging
Week 6
Set up Roster Front End
Set up Roster functionality
Debugging
Week 7
Set up Attendence page
Configure attendence functionality
Debugging
Week 8
Finish configuring application functionality
Debugging
Week 9
UI Improvement
Debugging
Week 10
Testing/ fine tuning
Debugging
Creating Final Presentation